## NCL Action Plan
Action Plan 2026-2027
Objective (reference 1.1) | SFC Priority Outcome (Original) | College Key Strategic Themes | Lanarkshire Regional Strategy (removed as out of date) | Lanarkshire Outcome Agreement 2023-2024 (Priorities) | Public Procurement Strategic Objectives | Procurement Outcomes | Main Actions & Commitments | KPIs/Benchmark Data | Annual Review | Responsibility | Priority H/M/L | PCIP Reference | Status July 25
To sustain and further develop partnerships within the sector, with other publicly funded bodies, with professional bodies and appropriately with supply markets that will yield intelligence, innovation and deliver value to users of procurement services |  | The Centre for Lanarkshire’s Public Service Education | Inspirational Learner Journey | High Quality Learning and Teaching Student Interests, Access and Success Financial Viability/Sustainability | Good for Businesses and their Employees - Suppliers - Supply Chain and Resilience Open and Connected - Global Reach | Optimised use of Cat A, B and C1 collaborative contracts and extension of early procurement contributions of value to all areas of "influenceable" expenditure | Scrutinise annual expenditure analysis to improve its effectiveness. Identify collaborative regulated procurements and categorise. Maintain the Contracts Register | Numbers and values for A, B and C1 as a % |  | Procurement Manager | Priority | Dashboard 2.1 3.3 | Currently in Progress for 25/26 - Awaiting on report from Finance
[6 empty] | Establish network with APUC, other sector consortia, sector representatives bodies for collaborative and professional development | Benchmarking of good practice standards and procurement performance standards | PCIP Score |  | Procurement Manager |  | 1.5 | Procurement Manager continues to attend all Procurement Strategy Group - College (PSG-C). APUC Ltd Open Forums and Networking Conferences.
[6 empty] | Extension of best practice methods and ethical values to all phases of the procurement process | Update procurement policy and procedures on an annual basis ensuring alignment to Procurement Journey. Update training as required. | Details of training delivered and numbers involved |  | Procurement Manager |  | 1.4 | Further training on procurement polices and procedures was delivered to Professional Service Leaders and Academic leaders in May 2025 with a total of 21 attending. Moodle training course has been developed and live to be rolled out to staff Start of August.
[6 empty] | Development of a shared, integrated procurement strategy development process | Maintain forward contracting plan and strategies and relate these to sectoral, regional and national contracting plans | Number and value of contracts covered by contracting strategies |  | Procurement Manager |  | 1.2 2.1 | Since April 2025 we have let have not awarded contracts with a procurement strategy. A few have been approved but the requirement has either been cancelled or delayed.
Objective (reference 1.2) | [5 empty] | Outcomes | Main Actions & Commitments | KPIs/Benchmark Data | Annual Review | Responsibility | Priority | PCIP Ref
H/M/L
To work with internal academic budget holders professional support service colleagues and suppliers to deliver innovation and best value to the learning, research and service support communities through the development of an effective and co-ordinated purchasing effort within the College | Inspirational Learner Journey An outstanding system of Learning. A more successful economy and society. | The Centre for Lanarkshire’s Public Service Education | Inspirational Learner Journey | High Quality Learning and Teaching Financial Viability/Sustainability Student Interests, Access and Success Good Governance | Good for Businesses and their Employees - Suppliers Good for Society -Economic Wellbeing Open and Connected - Connectivity - Consistency | Procurement information routinely communicated to people who need to know | Co-ordinate procurement initiatives and disseminate procurement information from external sources e.g. APUC contract and advisory information. Launch of Procurement Hub and optimise use once embedded. | Frequency and forms of communications. |  | Procurement Manager | MEDIUM | Dashboard 1.5 | Procurement Hub on the clan is now up to with all college and procurement policies and procedures. Also an email is due to be sent out in August 2025 to all budget holders giving information on policies and procedures as refresher for new academic year.
[6 empty] | Procurement engagement with key stakeholders | Meet with key stakeholders annually to provide procurement update, forward plan for their area and receive feedback on procurement service. | Annual meetings complete and outcomes actioned. |  | Procurement Manager |  | 1.1 1.5 | Monthly meetings take place between Procurement Manager and Head of Estates and Head of ICT (separate meetings) as the 2 x biggest spend depts at the College. Also bi-weekly meetings between Procurement manager and financial controller.
[6 empty] | Procurement training and/or guidance systematically applied to points of needs | Ensure all staff involved in procurement process can receive appropriate training | Record of staff attending individual training events, also to include counter fraud and conflict of interest issues |  | Procurement Manager |  | 1.4 1.6 | Procurement training was delivered by Procurement team to Academic Leaders and Professional Service leaders in May 2025. This was also logged on the NCL training log. SB also developed a Moodle procurement training course which will go live in August.
[6 empty] | Implementation of efficient procurement processes e.g. tendering, requisitions, approvals, order and invoicing processes | Robust internal control systems for procurement processes and systems including systematic use of PCS and PCS-T Review credit card spend to identify areas that can be moved to PO process | Clean Audit Report Identified suppliers moved to PO process |  | Procurement Manager |  | 4.1 1.6
[6 empty] | Suppliers and potential suppliers provided with guidelines and advice on doing business with the College and APUC | Clear communication on procurement issues and links on website | External website up to date at all times |  | Procurement Manager |  | 3.1 3.2 | External Website is up to date with all correct procedures and strategies.
Objective (reference 1.3) | [5 empty] | Outcomes | Main Actions & Commitments | KPIs/Benchmark Data | Annual Review | Responsibility | Priority | PCIP Ref
H/M/L
To promote the delivery of value for money through good procurement practice and optimal use of procurement collaboration opportunities | [5 empty] | Robust procurement policies and procedures in place | Review and update tendering policy and associated procedures to align to current best practice | Policy and procedure review and updates complete |  | Procurement Manager |  | 1.1 | Policies updated on external New College Lanarkshire website and all shown on the clan for internal staff. No reviews of policies currently required
| Effective & Efficient A more successful economy and society and Strong & Sustainable High Performance institutions. | The College to drive the Lanarkshire Economy Leading Lanarkshire Sustainable future | Effective and Efficient Strong and Sustainable | High Quality Learning and Teaching Financial Viability/Sustainability Good Governance | Good for Businesses and their Employees -Suppliers -Supply Chain and Resilience -Contract Management Good for Society -Economic Wellbeing | Clear specifications and procurement strategies agreed with stakeholders Regular review of the need for and performance of contracts prior to developing replacement procurement strategies | Review organisational expenditure data to identify contracts in place, contracts with stakeholder agreed strategies, regulated procurements. Training of organisational staff on best practice including appropriate approaches to regulated procurements in use of specifications, selection and award criteria | %s of total expenditure covered by CAT A,B, C1 & C contracts |  | Procurement Manager | HIGH | Dashboard 2.1 2.2 | In progress for 25/26
[6 empty] | Category contract strategies that detail the organisational approach to regulated procurements | Expenditure data sorted into categories | % of compliant expenditure by category |  | Procurement Manager |  |  | To be actioned - discussions have been had for categories strategies with estates and ICT as the two biggest spend departments
[6 empty] | Management and measurement of performance of contracts in line with stakeholder and supplier agreements over the lifetime of the contracts | Develop commodity strategies in line with the Procurement Journey. Contract and supplier management processes applied to all significant provision and associated suppliers. Joint feedback sought from suppliers and College securing service improvement and/or opportunities for innovation. | Service improvements through contract management documented. |  | Procurement Manager |  | 2.2 3.3 2.3 3.1 3.2 | In progress - active contract management will continue taking place for Blue Bus, Key Travel, Minor Works framework, Taxi Services, Agilco
[6 empty] | Periodic and annual savings and benefits reported to SMT and stakeholders | Recorded savings and benefits calculated according to agreed sector and national criteria. Reports to Management & Stakeholders | £value savings or other efficiencies i.e. cash and non-cash savings |  | Procurement Manager |  | 1.5 | Benefits Statement currently in progress
Objective (reference 1.4) | [6 empty] | Main Actions & Commitments | KPIs/Benchmark Data | Annual Review | Responsibility | Priority | PCIP Ref
H/M/L
To seek out professional development opportunities to enrich and enhance experience and capability of procurement practitioners and to work with the supply chains to ensure continued value, managed performance and minimal risk throughout the life of contracts for the benefit of customers and students | Develop & Nurture A more equal society. A culture of enterprise and innovation. | Driving better student outcomes | Develop & Nurture | High Quality Learning and Teaching Skills and Work Based Learning Good Governance | Open and Connected - Global Reach -Consistency Good for Businesses and their employees -Suppliers -Supply Chain and Resilience | A high calibre procurement team with competency based training and skills development programmes. Structured recruitment, career development and retention programmes | Conduct high level analysis of procurement competencies and skills profiles required at different levels of procurement engagement and conduct gap analysis | Number of people in the procurement team Number of procurement officers with MCIPS or MSc per £m of influenceable expenditure |  | APUC Ltd Senior Supply Chain Manager | MEDIUM | Dashboard 1.3 | AI has level 4 CIPS and has completed part of level 5. SB working towards MCIPS through experience due to university degree which allows this after 3 years.
[6 empty] | Procurement Risk Register in place | Develop a Procurement Risk Register | Procurement Risk Register in place |  | Procurement Manager |  | 1.6 | To be actioned
[6 empty] | Devolved procurement competencies assessed across the College Procurement induction programmes for all new appointees | Address shortfall by encouraging involvement with or attendance at training and development courses and events with results monitored and recorded | Number of authorised or delegated purchasing staff outside procurement per £m of influenceable expenditure. Number of procurement officers to have undertaken formal training & development in the past year |  | Procurement Manager |  | 1.4 | SB regularly attends APUC training including finance for procurement training, modern slavery and category management
Objective (reference 1.5) | [6 empty] | Main Actions & Commitments | KPIs/Benchmark Data | Annual Review | Responsibility | Priority | PCIP Ref
H/M/L
To develop sound and useful procurement management information in order to measure and improve procurement and supplier performance in support of corporate planning conducted through fair and transparent process | Effective & Efficient A more successful economy and society. | The College to drive the Lanarkshire economy | Effective & Efficient | Equalities, Diversity and Inclusion Good Governance | Open and Connected -Connectivity -Consistency | Use of benefits measurements to record efficiencies generated by procurement activity | Adopt efficiency measurement model | Hunter in full use. Annual Savings Report from Hunter. |  | Procurement Manager | HIGH | Dashboard 2.3 1.5 1.2 | Hunter in full use and kept up to date
[6 empty] | Annual report records achievement against strategic objectives | Prepare periodic reports that address both management needs and the requirements of the PRA. Prepare annual report on performance against procurement strategy. | Annual Report Trend Analysis |  | Procurement Manager |  |  | Annual report to be actioned when required.
Objective (reference 1.6) | [6 empty] | Main Actions & Commitments | KPIs/Benchmark Data | Annual Review | Responsibility | Priority | PCIP Ref
H/M/L
To embed sound, ethical, social and environmental policies within the Institution’s procurement function, to respond to the global climate emergency and to comply with relevant Scottish and UK legislation in performance of the sustainable procurement duty. | Strong & Sustainable High Performance institutions. | Leading Lanarkshire Sustainable Future | Strong & Sustainable | Net Zero Equalities, Diversity and Inclusion | Good for Places and Communities - Community Wealth Building - Fair Work First and Community Benefits - Supporting a sustainable built environment - Community Participation - Climate Crisis and Environment - Whole Life Costing Open and Connected -Consistency Good for Businesses and their Employees -SMEs, Third Sector and Supported Businesses Good for Society - Economic Wellbeing - Food Security | Achieve social and environmental benefits through policy, frameworks and local contracts Contribute to Climate Emergency Agenda. Take account of Climate and Circular Economy in procurement activity. | Embed social and environmental criteria in mini competitions and local contracts. Use tools available to identify relevant criteria. Supply Chain Code of Conduct included and signed by appointed Contractor(s) Investigate use of supported businesses/social enterprises/SMEs for relevant contracts Publish annual Modern Slavery Statement Consider innovation in each local tender giving consideration to new approaches Support the College to have in place, From Now to 2030 (FNT2030) action plans aligned to the Supply Chain Climate & Ecological Emergency Strategy Maintain Community Benefits Tracker | BT14 Benefits on an annual basis Achievement of modern slavery statement procurement actions Use of supported business/social enterprises Use of SMEs Innovative approaches Sustainability positive impacts e.g. climate change, circular economy derived from procurement/input activity Progress on FNT2030 Action Plans Community Benefits Delivered |  | Procurement Manager | HIGH | 2.4 | Benefits Statement currently in progress No supported businesses used Spend with SMEs to be confirmed by DXC FNT2030 Action Plans in progress

## Public Proc Strategy Objectives
Public Procurement Strategy Objectives - 2023-2028
| Good for Business and their Employees | Good for Places and Communities | Good for Society | Open and Connected
| Maximise the impact of procurement to boost a green, inclusive and wellbeing economy, promoting and enabling innovation in procurement. By Business we include any organisation or enterprising entity engaged in commercial, industrial, or professional activities including, voluntary, charity, for – profit and non-profit entities. | Maximising the impact of procurement with strong community engagement and development to deliver social and economic outcomes as a means to drive wellbeing by creating quality employment and skills. | Ensure that we are efficient, effective and forward thinking through continuous improvement to help achieve a fairer and more equal society. | Ensure procurement in Scotland is open, transparent and connected at local, national and international levels.
| Suppliers Promoting early supplier engagement to foster innovative and entrepreneurial responses to Public Sector needs and requirements. Collaborating with organisations to deliver positive, green and inclusive social impacts within public contracts. Having a holistic approach with key suppliers. | Community Wealth Building - Fair Work First and Community Benefits Maximising economic and social benefits through procurement and commissioning, applying fair work practices, developing good enterprises, and secure supply chains. | Economic Wellbeing Make conscious and considered decisions that achieve best value and aims to establish practices and contracts that support the people and organisations of Scotland. | Global Reach Remain connected to support development of best practice.
| Supply Chain and Resilience Encouraging a sustainable supply base that can support the work of the Public Sector to provide resilient and robust supply chains. Developing appropriate relationships and putting forward looking plans in place to support the development of the Supply Markets, improving security of supply and reducing risk. | Supporting a sustainable built environment Maximising opportunities in procurement to develop, enhance and maintain a sustainable built environment. Creating a portfolio of frameworks delivering a range of construction activity across the public sector which considers the economic impact and the sustainability of the construction industry and the requirement for inclusive growth and climate change targets. Ensure construction projects reflect and help deliver all pertinent Scottish Government obligations including Fair Work First and Net Zero. Actively consider issues including but not limited to Fair Work First and Net Zero early in procurements and commissioning activity. | Emergency situations Procurement has been critical in responding to previous emergencies and humanitarian situations, and will strive to provide innovative, effective and efficient responses to future emergency situations. | Connectivity We will strive for an ease of doing business with the Public Sector and for the Public Sector to be able to easily do business with our suppliers. Take advantage of opportunities to develop and improve the data, management information and systems, while leveraging automation and future technologies.
| SMEs, Third Sector and Supported Businesses Consider how procurements are conducted and contracts are developed, to reduce barriers and enable participation for SMEs, Third Sector organisations, and Supported Business, in Public Sector Procurement. | Whole life costing Promoting sustainable procurement through routine consideration of whole life costing to ensure value for money in procurement, minimise environmental damage and maximise socio-economic benefits. | Food security Ensuring high standards of animal welfare and sustainable production and waste reductions through the procurement process to improve community health, wellbeing and education. | Consistency Promoting consistent use of tools, platforms and systems, processes, guidance and templates.
| Contract Management Carrying out ongoing proportional contract management to ensure the right outcomes are delivered and the performance of contracts is maximised. | Community Participation Engaging with communities to understand local needs and requirements to help shape procurement policies, initiatives and contracts.
Climate Crisis and Environment Making informed decisions as we engage early with suppliers to create innovative solutions to positively respond to the climate crisis. Eliminating waste throughout the supply chain where possible. Act in a way that will secure net zero emissions through a Just Transition and promote a circular economy.
Linked to Action Plan